## Project Information
PROJECT BASIC INFORMATION
Project Name | Huntd
Name of Product | The best app for hiring web3 developers.
| Links | Test plan | Permission table | RTM
|  | Jira | TestRail WEB | TestRail Mobile
Product Description | Huntd is a comprehensive job search and application tracking app designed to assist job seekers in their quest for employment. With its user-friendly interface and powerful features, this app is essential for individuals actively seeking job opportunities.
Project Description | Mission of the project | Conduct testing to verify the quality of the web and mobile application.
Ensure the application is released without defects.
| Project output product | Test Summary report and Defects evaluation
| Project Type | Testing
Project Duration | Start date | 2025-10-03 | End date | 2025-11-24
Test Objectives | The test objectives are the functionality of the web version and mobile version of the “Huntd”. The project focuses on the possibility to interact with the main objects of the website and app.
The test objectives are to verify the functionality of both the web and mobile versions of the “Huntd” platform. The focus is on ensuring that users can interact correctly with the main objects, forms, and navigation elements on both platforms.
For Website – Main Objectives: 1. Verify that all primary navigation elements (header, footer, menus) function correctly. 2. Verify that user authentication flows work properly: Sign Up, Sign In, Password Recovery. 3. Verify that profile creation and editing (Candidate / Recruiter) work and save correctly. 4. Verify that main sections (Jobs, Chats, Preferences, Notifications) are accessible and functional. 5. Verify that interactive objects (buttons, links, dropdowns, selectors) behave as expected. 6. Verify that form validation works correctly (email, password, salary, location, etc.). 7. Verify that search and filter functionality works as expected (jobs, candidates, recruiters). 8. Verify that external links (LinkedIn, GitHub, Behance, social media) open correctly. 9. Verify that responsive layout and UI elements adapt to different screen sizes.
For Mobile App – Main Objectives: 1. Verify that the mobile app supports Candidate and Recruiter workflows correctly. 2. Verify that Sign Up / Sign In / Password Recovery flows work as expected on iOS and Android. 3. Verify that profile management (ROLE, EXPECTATIONS, EXPERIENCE for Candidate; My role, Company for Recruiter) works correctly. 4. Verify that Chats section displays all and archived conversations properly. 5. Verify that Notifications and Preferences can be configured and saved. 6. Verify that interactive UI elements (buttons, dropdowns, selectors, sliders) work as intended. 7. Verify that form inputs enforce validation rules (email format, password strength, numeric fields). 8. Verify that the profile type selection (Candidate / Recruiter) functions correctly after Sign Up. 9. Verify that location selector and salary input fields work and update correctly. 10. Verify that external links open correctly in the mobile environment.

## Test Summary
Execution Rate for Huntd Web app | [8 empty] | Execution Rate for Huntd mobile app
Executed test cases |  | 216 | 100% | [5 empty] | Executed test cases |  | 122 | 100%
Passed |  | 153 | 70.83% | [5 empty] | Passed |  | 104 | 85.25%
Failed |  | 45 | 20.83% | [5 empty] | Failed |  | 11 | 9.016%
Blocked |  | 18 | 8.333% | [5 empty] | Blocked |  | 7 | 5.738%
Huntd Web bugs by Priority
Critical |  | 11 | 24.44%
High |  | 17 | 37.78%
Medium |  | 12 | 26.67%
Low |  | 5 | 11.11%
Web features | [8 empty] | Mobile features
No. | Features | Tests | Passed |  | Failed |  | Blocked |  | No. | Features | Tests | Passed |  | Failed |  | Blocked
1 | Main page | 24 | 20 | 83.33% | 4 | 16.67% | 0 | 0% | 1 | Main page (Sign In screen) | 21 | 17 | 80.95% | 3 | 14.29% | 1 | 4.762%
2 | Candidate list | 30 | 25 | 83.33% | 5 | 16.67% | 0 | 0% | 2 | Sign Up | 22 | 17 | 77.27% | 3 | 13.64% | 2 | 9.091%
3 | Sign Up | 78 | 47 | 60.26% | 17 | 21.79% | 14 | 17.95% | 3 | Profile | 75 | 66 | 88% | 5 | 6.667% | 4 | 5.333%
4 | Sign In | 21 | 16 | 76.19% | 5 | 23.81% | 0 | 0% | 4 | Chats | 4 | 4 | 100% | 0 | 0% | 0 | 0%
5 | Chats | 14 | 11 | 78.57% | 3 | 21.43% | 0 | 0% | 5 |  |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
6 | Profile | 11 | 7 | 63.64% | 1 | 9.091% | 3 | 27.27% | 6 |  |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
7 | Footer | 15 | 10 | 66.67% | 5 | 33.33% | 0 | 0% | 7 |  |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
8 | Web3 companies and Jobs | 23 | 17 | 73.91% | 5 | 21.74% | 1 | 4.348% | 8 |  |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!
| Latest (Coverage) | 216 | 153 | 70.83% | 45 | 20.83% | 18 | 8.333% |  | Latest (Coverage) | 122 | 104 | 85.25% | 11 | 9.016% | 7 | 5.738%

## Test Data
Role | Email | Password
recruter | companyt@gmail.com | fAC4eDQ2cpHfvf$
engineer | engineertest@gmail.com | AV6XMDd7C$UJLxU